## Web Bug Report
Sl No | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Status | Link | Status (Developer)
1 | Error creating account with valid details | 1. Navigate to Create Account page 2. Fill all mandatory fields (Name, Email, Mobile, Password, Confirm Password, etc.) with valid data 3. Click on Create Account/Register button | Account should be created successfully and user redirected to login or dashboard page with success message | Error message "Error creating account" displayed; account is not created | High | Critical | Open | Video Evidence | Not Fixed
2 | Username field accepting numbers and special characters; Password field missing validations and eye icon | 1. Navigate to Create Account page 2. Enter numbers and special characters in Username field 3. Enter numeric-only password 4. Check for eye icon | Username field should restrict invalid characters and display validation message; Password should have strength validation and eye icon | Username field accepting invalid inputs without validation; Password field accepting weak passwords and no eye icon present | High | Major | Open | Video Evidence | Not Fixed
3 | Unnecessary menu items displayed on Create Account page | 1. Navigate to Create Account page 2. Check top menu/navigation bar | Only relevant options (e.g., Login, Help) should be displayed; unnecessary options (Home, Product, Contact, Favorites, Cart) should be hidden | Irrelevant menu items are displayed (Home, Product, Contact, Favorites, Cart) | Medium | Moderate | Open | Video Evidence | Not Fixed
4 | Footer and social media links not functional on Create Account page(Everywhere) | 1. Go to Create Account page 2. Scroll to footer section 3. Click on each social media link and Quick Links | All links/icons should redirect properly to respective pages | All links and icons are non-functional; nothing happens when clicked | Medium | Major | Open | Video Evidence | Not Fixed
5 | Sign Up not working; Login & Forgot Password cannot be tested | 1. Attempt to Sign Up with valid details 2. Attempt Login with registered credentials 3. Attempt Forgot Password using email | Sign Up should work and allow login and password reset | Sign Up fails; Login and Forgot Password cannot be tested due to failed registration | High | Critical | Open | Screenshot Attached | Not Fixed
6 | Email textfield accepting uppercase letters in Sign Up page | 1. Navigate to Sign Up (Create Account) page 2. Enter email address in uppercase letters (e.g., TEST@GMAIL.COM) in the Email field 3. Try to submit the form | Email field should automatically convert input to lowercase or show validation error for uppercase letters (if restricted) | Email field accepts uppercase letters without any validation or auto-conversion to lowercase | Medium | Major | Open | N/A (Let me know if you want to add a video/screenshot link) | Not Fixed
7 | "View All" button in Home Page redirects to 404 error page | 1. Navigate to Home Page 2. Click on "View All" button under any section (e.g., Events, News, Rooms) | Should redirect to respective full list page (e.g., All Events, All News, All Rooms) without error | Redirecting to 404 error page | High | Major | Open | https://somup.com/cTeIDL7gvV | Not Fixed
12 | After adding a product to the cart, increasing quantity , decrease button is unclickable, and size is not displayed.We can increase only 2 quntity | 1. Add a product to the cart. 2. Open the cart page. 3. Click on the increase quantity button. 4. Click on the decrease button. 5. Check if the product size is displayed. | - Quantity should update correctly when increased or decreased. - Decrease button should be clickable. - The selected size should be displayed. | - When increasing the quantity,We can increse the quntity 2 only - The decrease button is disabled/unresponsive. - The size of the product is not displayed in the cart. | High | Critical | Open |  | Pending
8 | Cart showing blank page after adding product from Home Page | 1. Navigate to Home Page 2. Add any product to the cart by clicking "Add to Cart" 3. Click on the "Cart" icon or link on the Home Page header | Cart page should open displaying added product(s) with details like name, price, quantity, and checkout option | Cart page opens but appears blank with no content shown | High | Major | Open | https://somup.com/cTeID97gvA | Not Fixed
9 | "Add to Cart" button is not clickable in Cart Page | 1. Navigate to Cart Page directly or via Home Page 2. Try to click on "Add to Cart" button available on the Cart page (if visible) | "Add to Cart" button should be clickable, allowing users to add products directly from the Cart page (if designed to function that way) | "Add to Cart" button is not clickable or unresponsive | High | Major | Open | https://somup.com/cTeIbn7gwf | Not Fixed
10 | Pagination dots/progress indicator not visible on specific page | 1. Navigate through the application pages (Home, Product, Cart, etc.) 2. Observe the presence of pagination dots/progress indicators while navigating sections that require it | Pagination dots/progress indicators should be visible on all applicable pages (like sliders, carousels, multi-step forms) to indicate user's position | Pagination dots/progress indicator not highliting on specific page (as shown in video) | Medium | Moderate | Open | Video Evidence | Not Fixed
11 | Delete button size issue and Add to Cart button not clickable on Wishlist page | 1. Navigate to Wishlist page 2. Observe the Delete button size (should be easily clickable) 3. Try clicking Add to Cart button for any wishlist item | Delete button should be appropriately sized and visible Add to Cart button should be clickable and should add item to cart | Delete button is too small Add to Cart button is not clickable or unresponsive | High | Major | Open | https://somup.com/cTeIbi7gwK | Not Fixed
12 | Currency mismatch on Product page (Dollar & Rupees displayed together) and not able select the size | 1. Navigate to Home Page 2. Click on any Product to open Product Details Page 3. Observe the pricing format at the top and bottom of the page | The currency should be consistent across the product page (either Dollar or Rupees as per region settings) | Dollar ($) is shown at the top, and Rupees (₹) is shown at the bottom for the same product,and not able to select the size | High | Major | Open | https://somup.com/cTeIbX7gxh | Not Fixed
13 | Product details text is displaying incorrectly on Product Page | 1. Navigate to Home Page 2. Click on any Product to open Product Details Page 3. Scroll down to view Product Details section | Product details should be accurate, meaningful, and formatted properly | Product details are displaying incorrect, irrelevant, or broken text | High | Major | Open | https://somup.com/cTeIbo7gxk | Not Fixed
14 | Reviews inside text is not clear and "See All Reviews" button is not clickable | 1. Navigate to Home Page 2. Click on any Product to open Product Details Page 3. Scroll down to the Reviews section 4. Try to click on See All Reviews | Reviews text should be properly formatted and readable See All Reviews button should be clickable and open full reviews list | Reviews inside text is not clearly visible (broken formatting/overlapping) See All Reviews button is not clickable/unresponsive | High | Major | Open | https://somup.com/cTeIbF7gyf | Not Fixed
15 | Clicking on "Brand Collaboration" ( View Collection) in Home shows a 404 Error | 1. Open the home page. 2. Click on the Brand Collaboration section/link. 3. Observe the page response. | The Brand Collaboration page should load correctly. | Clicking the link results in a 404 error (Page Not Found). | High | Major | Open |  | Not Fixed
15 | "More from Fluid Line" section - Add to Cart not working and "See All" gives 404 error | 1. Navigate to Product Details Page 2. Scroll to "More from Fluid Line" section 3. Try clicking Add to Cart button 4. Click on See All link | Add to Cart button should add the product to cart See All should redirect to list of all related products without error | Add to Cart button is not functional Clicking See All leads to 404 error page | High | Major | Open | https://somup.com/cTeIb07gyk | Not Fixed
16 | Follow button and navigation arrows not clickable on Product Page(Everyever) | 1. Navigate to Home Page 2. Click on any Product to open the Product Details Page 3. Try clicking on Follow button 4. Try using arrow marks to navigate product images | Follow button should be clickable and allow following the product/brand Arrow marks should allow users to navigate product images | Follow button is unresponsive and not clickable Arrow marks for image navigation are not functional | High | Major | Open | https://somup.com/cTeIbt7g4f | Not Fixed
17 | Home link not highlighting active page and navigation links (Products, About, Contact) not working | 1. Open the website Home Page 2. Click on Home link and observe if it highlights 3. Click on Products, About, Contact links | Home link should be highlighted to indicate current active page Products, About, Contact links should redirect to respective pages | Home link is not highlighting active page Products, About, Contact links are non-functional (no redirection on click) | High | Major | Open | https://somup.com/cTeIbv7g4T | Not Fixed
18 | Wishlist page "Continue Shopping" button redirects to Home Page instead of Products/Shop Page.Image also not displaying | 1. Go to Wishlist Page 2. Click on Continue Shopping button | Continue Shopping should redirect user to Product listing/Shop Page to continue shopping | Continue Shopping button redirects to Home Page, not to product listing.Image also not displaying | Medium | Moderate | Open | https://somup.com/cTeIbB7gar | Not Fixed
19 | Home page, Store page & Cart page displays money in rupees (₹) instead of dollars ($) | 1. Open the home page & cart page. 2. Check the displayed currency for product prices and total amount. | The currency should be displayed in dollars ($) if the default currency setting is USD. | The Home page & cart page shows prices in rupees (₹) instead of dollars ($). | Medium | Major | Open |  | Not Fixed
20 | Change Password functionality is not working and Eye icon for password visibility is missing | 1. Go to Change Password page/section 2. Enter current password, new password, confirm new password 3. Click on Submit/Change Password button 4. Observe for Eye icon in password fields | 1. Password should be successfully changed with confirmation message 2. Eye icon should be visible to toggle password visibility | 1. Password is not getting updated, no confirmation message shown 2. Eye icon is missing in password fields | High | Major | Open | https://somup.com/cTeIbH7gzl | Not Fixed
21 | Delete Account button in Profile > Settings is not clickable | 1. Go to Profile Page. 2. Navigate to Settings. 3. Try to click the Delete Account button. | The Delete Account button should be clickable and initiate the account deletion process. | The Delete Account button is unresponsive and does not perform any action. | High | Major | Open | https://somup.com/cTeIbN7gzS | Not Fixed
22 | In Profile Page, Home, Products, About, Contact links are not fixed on scroll | 1. Go to Profile Page 2. Scroll down the page | Header links like Home, Products, About, Contact should stay fixed at the top while scrolling | Header links are scrolling along with the page and not staying constant | Medium | Moderate | Open | https://somup.com/cTeIbK7gz4 | Not Fixed
23 | Clicking on Ted Dot in Explore Brands navigates to the page, but the name is not displayed, and the tagline "Comfort with Confidence" is shown instead of products. | 1. Open the Home Page. 2. Scroll to the Explore Brands section. 3. Click on Ted Dot. 4. Observe the page navigation and displayed content. | The page should display the Ted Dot brand name and show its products. | The Ted Dot brand name is missing, and instead of products, it shows "Comfort with Confidence." | Medium | Major | Open | https://somup.com/cTeIFf7gBj | Not Fixed
24 | Jelante product page image is not displaying and no description | 1. Navigate to Home/Product listing page 2. Click on Jelante product | Product page should display complete product details including name, description, price, specifications, etc. | image is not displayed; "No description available" message is shown | High | Major | Open | https://somup.com/cTeIbR7gA4 | Not Fixed
25 | Clicking on Fluid Line in Explore Brands navigates to a page where the name is displayed lightly & the logo is missing. | 1. Open the Home Page. 2. Scroll to Explore Brands section. 3. Click on Fluid Line. 4. Observe the page. | The Fluid Line page should display the name clearly and include the brand logo. | - The Fluid Line name is displayed too lightly (low visibility). - The logo is missing from the page. | Medium | Minor | Open | https://somup.com/cTeIFl7ggc | Not Fixed
26 | In Home Page, selecting any Brand Collaborations link redirects to 404 error page | 1. Navigate to Home Page 2. Scroll down to Brand Collaborations section 3. Click on any brand | User should be redirected to respective brand collaboration details page | Redirecting to 404 error page | High | Major | Open | https://somup.com/cTeIFQ7gBE | Not Fixed
27 | Alignment issue in New Arrival section on Home Page | 1. Navigate to Home Page 2. Scroll down to New Arrival section | All product cards/items should be aligned properly in a uniform grid layout, without overlapping or misalignment | Products in the New Arrival section are misaligned | Medium | Moderate | Open | https://somup.com/cTe2hx7ktW | Not Fixed
28 | Full Name, City, and State fields in Shipping Information accept numeric values & special characters. | 1. Go to the Cart Page. 2. Click on Proceed to Checkout. 3. Navigate to the Shipping Information page. 4. Enter numeric values and special characters in Full Name, City, and State fields. 5. Observe the input behavior. | - The Full Name, City, and State fields should accept only alphabetical characters. - Numeric values and special characters should not be allowed. | - The fields accept numbers (123) and special characters (@#$%^&*), which is incorrect. | High | Major | Open | https://go.screenpal.com/watch/cTe2hLn1PSU | Pending
29 | Changing Address on Payment Page Clears Shipping Information Data | 1. Go to the Cart Page. 2. Click on Proceed to Checkout. 3. Navigate to Shipping Information. 4. Fill in all shipping details and click Continue to Payment. 5. On the Payment Page, click Change Address. 6. Observe the Shipping Information page. | The Shipping Information page should retain the previously entered data. | The Shipping Information page appears empty (data is lost). | High | Major | Open | https://somup.com/cTe21X7kvo | Pending
30 | Clicking on Payment navigates to Contact Details, and the UPI price is incorrect compared to the product price summary. | 1. Add products to the cart. 2. Proceed to checkout. 3. Click on the Payment button. 4. Observe if it navigates correctly. 5. Check the UPI price and compare it with the product price summary. | - Clicking Payment should navigate to the correct payment page. - UPI price should match the product price summary. | - Payment button incorrectly navigates to Contact Details instead of the payment page. - UPI price does not match the product price summary. | High | Major | Open | https://somup.com/cTe21A7kw5 | Pending
31 | "Chill Guys" image is not proper, incorrect size, and not clickable | 1. Navigate to Home Page 2. Scroll down to "Chill Guys" section | Image should display properly, fit in design layout, and should be clickable if intended | Image appears distorted/improper size, and cannot be clicked | Medium | Major | Open | https://somup.com/cTe21E7kxQ | Not Fixed
32 | "Chill Guys" section 'See All' link redirects to 404 Error page | 1. Navigate to Home Page 2. Scroll to "Chill Guys" section 3. Click on 'See All' link | Clicking See All should open a page displaying all "Chill Guys" products | 404 Error page is displayed when clicking on See All | High | Major | Open | https://somup.com/cTe21J7kxT | Not Fixed
2025-03-17
1 | Product Quantity Mismatch Across Product Page, Cart Page, and Cart Icon | 1. Go to Product Page and add a product with multiple quantities (e.g., 5). 2. Go to Cart Page and check the added quantity. 3. Observe the Cart Icon on the Home page for quantity count. | User should be able to add multiple quantities consistently. Cart Page should reflect the same quantity as selected. Cart Icon should show correct total item count. | Cart Page limits to only 2 quantities, despite adding more on Product Page. Cart Icon displays wrong total items. | High | Major | Open |  | Not Fixed
2 | In home page, Add to Cart Limitation Message After 10 quantity | 1. Go to Home Page. 2. Click Add to Cart for any product repeatedly. 3. Try adding more than 10 quantities of the same product. | System should either restrict adding more than 10 quantity with a user-friendly message OR should allow more than 10 if no limit intended. Proper validation message should be shown if a limit is applied. | After adding 10 quantity, system throws error message: "Cannot add more than 10 items to the cart" in the home page & intead of quantity it showing as items in error. . | Medium | Moderate | Open |  | Not Fixed
3 | Cart Page Quantity Control Not Working Properly & Incorrect items Shown in Cart Icon | 1. Navigate to Home Page. 2. Add a product with quantity = 10. 3. Redirected to Cart page. 4. Try to increase or decrease the product quantity in Cart. 5. Observe the cart icon quantity on top right. 6. Check for error message shown when trying to adjust quantity. | 1. Should be able to increase or decrease quantity within allowed range (max 10). 2. Proper error message if trying to exceed limit. 3. Cart icon should reflect the correct total items. 4. Accurate items reflected inside cart page. | 1. Increase/Decrease buttons in Cart are not clickable. 2. Error message shown: "Cannot add more than 2 items", even though only 10 quantity is added. 3. Cart icon shows incorrect items (wrong count). | High | Critical | Open |  | Not Fixed
4 | Add to Cart shows 'No size available' from Home Page but Size selectable on Product Page (not clickable on M size) | 1. Go to Home Page. 2. Click Add to Cart button directly from product card. 3. Observe error message: "No size available". 4. Click on product to navigate to product details page. 5. Try to select M size and increase size/quantity. | 1. From Home Page, size selection should be prompted if required before adding to cart. 2. On Product Page, all available sizes (like M) should be selectable. 3. Proper flow for adding item with selected size to cart. | 1. Error message "No size available" shown when adding from Home Page. 2. M size is visible but not clickable/selectable on Product Page. 3. Size/Quantity increase working inconsistently. | High | Major | Open | https://somup.com/cTeb6q7EyB | Not Fixed
5 | Inconsistent Quantity Limit Between Home Page & Product Page | 1. Go to Home Page. 2. Click Add to Cart multiple times until it reaches 10 items — error message appears: "Cannot add more than 10 items". 3. Now click on the product to navigate to Product Page. 4. Increase quantity beyond 10 using quantity selector. | Quantity limit should be consistent across Home Page and Product Page — either restrict to 10 everywhere or allow if applicable. Proper error messages should be shown when limit exceeds. | 1. On Home Page, cannot add more than 10 items — error displayed correctly. 2. On Product Page, able to add more than 10 items — no validation enforced. 3. Inconsistent behavior between pages. | High | Major | Open | https://somup.com/cTeb6B7Ezu | Not Fixed
6 | Jelante Brand Image & Description Not Displaying in All Brands Section | 1. Navigate to the Home Page. 2. Scroll down to the All Brands section. 3. Locate the Jelante brand. 4. Observe the image and description. | The Jelante brand should display its image and description correctly. | 1. Jelante image is missing. 2. No description is displayed under the brand. | High | Major | Open | https://somup.com/cTeb6J7EBe | Not Fixed
7 | All Brands Section Displays 0 Products, But More Products on Clicking Brand | 1. Navigate to Home Page. 2. Scroll down to the All Brands section. 3. Observe the product count for each brand (e.g., "0 products"). 4. Click on any specific brand (e.g., Jelante). 5. Check the number of products displayed inside that brand. | Product count should correctly reflect the total number of available products under each brand on the Home Page itself. | On Home Page: 0 products displayed under each brand. On clicking a brand: Multiple products are shown, contradicting the initial count. | High | Major | Open | https://somup.com/cTeb6s7EBw | Not Fixed
8 | TED Dot brand on Home Page not showing any products on click | 1. Navigate to Home Page. 2. Scroll down to All Brands section. 3. Locate and click on TED Dot brand. | After clicking TED Dot, the respective products under this brand should be displayed. | No products are displayed after clicking TED Dot, showing empty or blank page. | High | Major | Open | https://somup.com/cTeb687Ege | Not Fixed
9 | Clicking 'View Collection' under Brand Collaboration shows 404 Error | 1. Navigate to Home Page. 2. Scroll down to Brand Collaboration section. 3. Click on View Collection button under any brand. | It should navigate to the selected brand's collection page and display all relevant products. | 404 Error page is displayed instead of the collection. | High | Major | Open | https://somup.com/cTeb6R7Eg0 | Not Fixed
10 | Store page filter textfield and brand textfield accepting only one letter at a time, requiring cursor click to add more | 1. Navigate to Store page. 2. Click on Filter textfield,brand textfield 3. Try typing multiple letters continuously. | User should be able to type multiple characters smoothly without having to click the cursor for every letter. | Only one letter is accepted at a time, to type the next letter user needs to click again in the textfield. | High | Major | Open | https://somup.com/cTebXn7Eg9 | Not Fixed
11 | Product Title is Missing above the textfield in Store Page | 1. Go to Store page. 2. Scroll to view listed products. 3. Observe each product card under image or above price. | Each product should display its Product Title/Name clearly above or below the image. | Product Title/Name is not displayed above the product textfield. | High | Major | Open | https://somup.com/cTebXD7EpN | Not Fixed
12 | Ratings filter allows selecting multiple ratings at once; should allow only one checkbox selection | 1. Go to Store page. 2. Scroll to Ratings filter section. 3. Click on multiple ratings (e.g., 3 stars and 4 stars). | User should be able to select only one rating at a time to filter products (single selection). | User can select multiple ratings at once; conflicting filters applied. | Medium | Moderate | Open | https://somup.com/cTebXq7ECw | Not Fixed
13 | Footer bar is inconsistently fixed during scrolling on Store Page | 1. Go to Store Page. 2. Start scrolling down and up the page. 3. Observe the footer bar behavior while scrolling. | Footer should either remain fixed (sticky) at the bottom or move consistently with the content when scrolling — consistent behavior is expected. | Footer sometimes stays fixed, sometimes scrolls away — inconsistent behavior. | Medium | Minor | Open | https://somup.com/cTebX07E5c | Not Fixed
14 | Contact Page: Name field accepting only spaces, numbers, and special characters without validation error | 1. Navigate to Contact Page. 2. Go to Name text field. 3. Enter only spaces, numbers (e.g., "123"), and special characters (e.g., "@#$%"). 4. Try submitting the form. | Name field should accept only alphabets and give error message for invalid input (like numbers, special characters, spaces only). | Name field accepts invalid data without showing any error message and allows submission. | High | Major | Open | https://somup.com/cTebXx7EEF | Not Fixed
15 | Contact Us Page: Email field accepting invalid formats like uppercase, starting with numbers, and leading spaces without error | 1. Navigate to Contact Us page. 2. Go to Email text field. 3. Enter email as uppercase letters (e.g., "TEST@GMAIL.COM"). 4. Enter email starting with numbers (e.g., "2345@gmail.com"). 5. Enter email with leading spaces (e.g., " 345@gmail.com"). 6. Try submitting the form. | Email field should: ✔ Convert uppercase to lowercase automatically or throw error. ✔ Restrict emails starting with numbers if business rule applies. ✔ Trim leading spaces automatically. ✔ Validate proper email format. ✔ Display error messages for invalid inputs. | Email field is accepting invalid formats without any validation error and allowing form submission. | High | Major | Open | https://somup.com/cTebXx7EEF | Not Fixed
16 | Contact Page: Send Message button not clickable even after filling all required fields | 1. Navigate to Contact Us page. 2. Fill in all required fields (Name, Email, Subject, Message) with valid data. 3. Try to click the Send Message button to submit the form. | After filling all mandatory fields, Send Message button should be clickable, and on click, the message should be submitted successfully with a success alert or message. | Send Message button remains inactive / not clickable even after filling valid data in all fields. Unable to submit the message. | High | Critical | Open | https://somup.com/cTebXy7EEy | Not Fixed
17 | Contact Page: 'Our Location', 'Call Us', and 'Email' links are not clickable | 1. Navigate to Contact Us page. 2. Scroll to Our Location, Call Us, and Email section. 3. Try clicking on address (location), phone number, and email address links. | Location should open map (Google Maps) when clicked. Call Us should initiate a call on supported devices. Email should open the default email app to send a mail (mailto link). | Nothing happens when clicking on any of the links (Our Location, Call Us, Email) — they are not interactive/clickable. | Medium | Major | Open | https://somup.com/cTebXa7EEN | Not Fixed

## Mobile Bug Report
Sl No | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity | Status | Link | Status (Developer)
Mobile
1 | Overlapping Menu on Home Page | 1. Navigate to Home Page 2. Observe the top menu/navigation bar when scrolling or hovering over elements | Menu should remain properly aligned and not overlap with other page content | Menu items are overlapping with other page elements, affecting readability and usability | High | Major | Open | Pending evidence link if needed | Not Fixed
2 | My Orders page shows item count as 0 but still displays a price | 1. Open the Menu. 2. Click on My Orders. 3. If there are no orders, check the displayed details. | If no items are in My Orders, the item count should be 0 and the price should not be displayed. | The item count is 0, but a price is still displayed incorrectly. | Medium | Minor | Open |  | Pending
3 | Clicking on View Details in My Orders navigates to Order Tracking, but the status alignment is incorrect. | 1. Open the Menu. 2. Click on My Orders. 3. Select an order and click on View Details. 4. Check the Order Tracking section. | The Order Tracking status should be properly aligned for readability. | The Order Tracking status is misaligned, making it difficult to read. | Medium | Minor | Open |  | Pending
4 | Clicking Back to Order in Order Tracking Status navigates incorrectly to the same page instead of the My Orders page. | 1. Open the menu and click on My Orders. 2. Click on View Details of any order. 3. Navigate to the Order Tracking Status page. 4. Click on Back to Order and observe the navigation. | Clicking Back to Order should navigate back to the My Orders page. | Clicking Back to Order redirects back to the Order Tracking Status page instead of My Orders. | Medium | Major | Open |  | Pending
5 | Two unnecessary menus appear on the home page, and clicking both at the same time may cause issues. | 1. Open the Home Page. 2. Observe that there are two menu buttons instead of one. 3. Try clicking both menu buttons simultaneously. | There should be only one menu, and clicking it should function correctly. | - Two menu buttons are present unnecessarily. - Clicking both menus at the same time may cause unexpected behavior. | Medium | Minor | Open |  | Pending
6 | Inconsistent Branding Name (Club/ClubUnplugged) and Logo Misalignment | 1. Navigate to multiple pages (Home, Product, Profile, Wishlist, etc.) 2. Observe the header branding name and logo alignment | Branding name should be consistent (either Club or ClubUnplugged) across all pages. Logo should be properly aligned on all pages. | Some pages show "Club", some show "ClubUnplugged". Logo is misaligned (shifting to left or right, not vertically centered) on some pages. | Medium | Moderate | Open | Pending screenshot or video evidence link if needed | Not Fixed
7 | Order tracking status displays a product even when no product is added, showing quantity as 1 and price as ₹9.99. | 1. Open the Menu. 2. Click on My Orders. 3. Navigate to My Orders page. 4. Click on View Details of an order. 5. Observe the Order Tracking Status. | - If no product is ordered, the Order Items section should be empty. - No quantity or price should be displayed for non-existent orders. | - Order tracking shows a product even when nothing was ordered. - Displays Quantity: 1 and Price: ₹9.99 incorrectly. | High | Major | Open |  | Not Fixed
8 | Images Not Displaying in Most Popular & New Arrival Sections | 1. Navigate to the Home Page. 2. Scroll to the Most Popular and New Arrival sections. 3. Observe if all images are loading correctly. | All products in Most Popular and New Arrival sections should display their respective images properly. | Some product images are missing or not loading in these sections. | High | Major | Open | Pending screenshot or video evidence link if needed | Not Fixed
Remaining same bugs mobile and web